## Tasks
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Camera | Have a unique camera animation (position, angle and field of view) for each possible deaths.
GUI | If press REWIND and not enough time magic, go to store
GUI | Fade in/out REWIND and SKIP buttons.
GAMEPLAY | Code rewind feature that works for all moves.
GAMEPLAY | Code handling falling of a cliff
EFFECT | Code dust puff when landing |  | DONE
EFFECT | Code dust trail when sliding (possibly using trail renderer)
GAMEPLAY | Possibly allow TURNs while sliding (but not changing lanes) |  | DONE
| Tutorial | include button to skip tutorial
Opening cut-scene
Main menu
Settings menu
Credits
Gamecenter integration
Store and IAP
Offerwall
Player objectives
Change avatar
Localize text
Progression map
Code score and possibly score multiplier and design score system
| Handle new high score | save high score, tell user | DONE
Consider allowing player to level up
Unlock new powers at each checkpoint
Code flying enemy succubus
| Code rewind button with button, text, progress bar, number of time magic potions available |  | IN PROGRESS
Code a time magic power bar
| finish run again screen, add stats, total, butttons to access other menus |  | IN PROGRESS
| Support 1,5,10 , 50 and 1000 points collectibles |  | IN PROGRESS
| Dont get up from a slide if there is something above your head |  | DONE
| Code level generator |  | DONE
Have an unbelievably difficult run to an Inn as an Easter egg
| Have an opening camera when player starts running |  | DONE
| Have a camera looking at the front of the player (Olympics style), when the player arrives at a village |  | DONE
| Try to NOT turn world | fps issue, skybox issue, Unity terrain issue, possibly lightmapping issue | DONE
| Code soft turns | Using bezier
| Add T-junctions | This where signs could be useful to distinguish direct route from indirect route with more loot
Finish decorating END tile esp. Since camera does 180
Have a badger or goffer that pops out of the ground and makes you stumble. There is a warning sign of earth being moved before he appears.
| Have a set piece per level like a church |  | DONE
Add cart obstacle
Have a difficulty setting used in Generate level to allow for more more difficult levels to be generated as well as having side (T-junction) side roads deliver more loot
Code Detours
Finish t-junction
Create cemetery level
Create obstacle chart per environment
Add ability to turn off all sounds
Add curves with bezier
Add hills
Dont allow for 2 back-to-back rivers
Adjust high scores versus level and versus grand total
getSegmentInfo instead of separate methods
Clean-up code
Possibly add water plane always centered around current tile
Bench where player can stop enjoy the view before starting running again
Code Wormhole spell to skip part of the run
Have runes on the world map. If you tap the correct runes, they glow can unlock something
Code 3 star per level system
a) never died
b) score exceeds level
c) achievement style (never used slide)
T-Junction: ability to fall off straight in cliff like temple run 2
Code detours
Code worm hole
Code meadow tile with flowers
Code sun shaft effect (Pro has a version)
Code unlock next section by either paying or by asking 3 friends
Code ability to send lives to friends
Code book of eveil sequence. A gap in the sky appears. Must close it before midnight of the hords of hell will invade
Code succusbus and hero on bench want to go for coffee sometime?
Faster resurrect
Skip and Resurrect buttons too close
Rename resurrect to Revive me
| Code boots of Jumping | Icon plus explanation when given. Does it use charges?
Code light wand
Code road lanterns lit only if sunset or night
Finish dragon dumping you in hay stack
How does the witch give the boots (or any thing else) to the player? Sliding box?
Proceduraly turn the Hero's head as he looks back once in a while
Code ragdoll
Blend run and sprint based on run speed
Adjust font size based on screen resolution. Does NGUI handle that for you?
handle retina
Handle onapplicationpause
cartoon road runner style fall
code 3 stars earned per level
add people to the world

## Bugs
Bug number | Description | Device | Status | Time estimate | Time remaining | Priority
1 | Sometimes side-moves instead of turning in dead end. |  | FIXED |  |  | MEDIUM
Note | Corridor width is 2 x lane width plus 2 times player's diameter, plus 2 times margin of 0.4 = 5.4
3 | If Home button pressed while paused, when you come back, some sounds are playing
4 | When using SHIELD and you hit a hard obstacle like a dead tree which has a rigid body (which turns to trigger), you get derailed from your track |  | FIXED
5 | When sliding, the magical sphere is not positioned correctly
6 | If collide with stumble while doing a side-move, character will start moving in diagonal |  | FIXED
7 | The magical sphere decreases in size during the resume countdown |  | FIXED
9 | Rotator eats up 5-10fps because of transparency most likely
11 | Add a message like Go! At the end of the rewind |  | DONE
12 | Recode camera shake to work even while the player is moving so I can add it to stumble.
13 | Do a water test with the addition of reflection to see how it looks and how the frame rate is affected.
14 | In some circumstances, when the player dies, the character goes through the geometry. Consider transforming character into ragdoll at that moment or changing the animation.
17 | If you die in the air, you dont fall because update and hence gravity is no longer called |  | FIXED
19 | The font for rewind and skip and pause/resume is too small |  | FIXED
20 | Lower volume of death scream
21 | Should music stop while the rewind/skip options are displayed? |  | FIXED
22 | When you restart the level, you can see the enemy briefly and the camera is not exactly positioned |  | DONE
23 | Add a PAUSE key to pause for testing. It is the W key. |  | DONE
24 | Add a START player waypoint and have a dropdown list to get the player to start from various locations to facilitate testing
29 | Consider tilt to change lanes |  | DONE
| Lerp on player turn |  | DONE
| Change anim speed based on run speed |  | DONE
| Sometines the death animation message prints out twice |  | FIXED
| Add brook sound |  | DONE
| Finish enemy rewind |  | ON HOLD
| Code, stumble twice and you are toast |  | DONE
| Coins should travel to the coin counter like in Running with Friends |  | DONE
| Some coins, esp. when sliding, are not picked up |  | FIXED
Sometimes, you will jump automatically when landing in the river instead of dying
Don't display a high score message while dying
Polish: have coins attracted my magnet accelerate towards player
Polish: finish portcullis. Have it bounce a little as it finally closes
Portcullis down speed should be adjusted with player speed so the difficulty level remains constant
| Slide sound interrupts coin pick-up sound |  | FIXED
| Multiple coin sounds can play at the same time |  | FIXED
| Distance and coin spinners take more than 2 seconds to spin if score is high |  | FIXED
There is no magnet active effect
Mecanim delay before anims start (run and attack)
call F renouf, c bouffrad, nad, dave tardiff and chum genevieve
| Sorceress and skeleton cast no shadows if shader is unlit |  | FIXED
Got bug slide in diagonal with permanent X
Mecanim add animation events to play laugh audio at exactly the right time for example
Music why is music soooo loud?
On leaving stats screen, distance (but not coins) goes to 0 before the game begins
| When arrive at finish line, if jumping, you will end up in the air. Check slide as well. |  | DONE
End of finish line cheer audio sometime heard on play again
Consider fading in/out stats screen
| Various river death bugs |  | FIXED
If rewind, cannot stop in midair or in a dead end. So BEFORE rewinding, go forward again until isGrounded is true and isDeadEnd is false, store that index and stop there.
Go! Text too small. Consider tapping to start again.
Died in river, rewinded, go! Immediately did a change lane right. Hit right wall.
| River flow UV not in correct direction versus player movement |  | FIXED
Meurt pas si frappe un mur de coin a tester
| Bug bout de la riviere slide a travers geometrie |  | CNR
Make arch wider
| Fall in river die but no screen rewind if you die a second time with play again |  | FIXED
Fix end look esp 180 cam
| Roadlabel should be next city |  | FIXED
| Bug -592 meters to reach safety of rivendell |  | FIXED
Hurrah you did it too short
| Part of green floor (maybe of end tile) was covering part of river tile |  | FIXED
If jump and fall in the river king will stop in the middle of the air
Bug Possibly after rewind, you cant collect collectibles
Rewind tiles disappear
Shield only lasts 5 seconds
| Some coinpacks are 180 |  | FIXED
Does your character level up? Is so what does he gain? Premium currency? In running with friends you get gems. You leveled up gems
The number of gems is in the top left screen. This is a saved value.
00-trigger to say you arrived at checkpoint handled in level manager
A) crowd cheers
B) witch gives you something
C) peasant girl winks at you
NOTE | Music needs to be in .wav format or else will be recompressed, try stream from disk
4-managed to jump out of the lanes and run on the grass
6-pont levis qui monte
7- a cow
8 - crossing sign
Duck family, gremlins, manga school girls, i see things when i get tired
10-Succubus
14-if die in the air deadtree rewind in the air
15-remember animationspeedmodifier to have anims play in rewind at same speed as in normal
Use a generic displaymessage for high score, rivendell and go!
17-code start menu
Shield sphere size esp. On second pickup can be incorrect
Occasionaly, when rewinding, we can be one tile short in the back and hence see the blue sky below our feet
Try to generate level during loading screen
Display a coin total icon on screen like Running with friends like +7 in a bouncy star
Combine star textures into 1 to reduce draw calls
Add carnivorous plant maybe?
If you land with your knees in the log, you stay floating in mid air
Sometimes, you cant turn after a rewind
After rewind, ended outside of path. Possibly because of turn
Minor lag breakable barrel-could instantiate particle system on awake
Make sure player arrives in the center lane at the finish line
Animate flag on defense tower
Have ambient sound crossfade to new sound when changing segment styles
Add a Log.warn when fps drops by more than 5 fps in single frame
Some tiles not appearing during rewind
fix move down river - work partially completed
After turn, set player in center of current lane
Bug when changing lanes, esp center to right, sometimes you jump to the final destination instead of reaching gradually
Add shadow to ocean
Ocean gets pixalated under certain conditions
Bug: sometimes (after bezier?) move direction x does not go back to zero
Bug: some barrels no longer spawn debris
Bug: remove unlit grass from tiles
Bug is PAUSE while dying
Concern: fire should have shadow in cemetery since hard to judge position
Bug: using accelerometer, I died by going right before the river. The code keep me in the corridor did not seem to work.
Bug: some times can press resurrect twice
Bug: arrived at castle in left lane. Suspect lanes incorrect when entering
Bug: if jump in the river and die, player will move in a diagonal and not with the current
Bug: if die because of stumble, stumble anim will play after revive
Performance: make the tile the parent of the spawned crow
Performance: consider resizing down the Achievement textures received by Game Center
BUG: sometimes T-Junction is at 90 degrees which should not happen
Consider room for banner ad in GUI design
BUG if connect to facebook does not remember

## Asset store
See
Monster base team
Medieval kingdom
Cute medieval warrior
Medieval props
White chicken

## Design
Endless runner inspirations
Tales of two son
Catapult king
How to train your dragon
Asset store:
#NAME?
#NAME?
#NAME?
Cusp of Autumn
Main characters
Postman
Succubus
Goblin king
Witch that gives upgrades to postman
Cow
Peasant guy
Peasant girl
Villager 1
Villager 2
Bird flying
Bird on post
Book of demons
Time of day can fluctuate as we go through various levels
5 settings:
Farmland
Swamp
Mountains
Elf circle
Cimetary
Village
King casle
Forest
City of trees elf style
City in the clouds
City over a river
Floating boat houses/lanterns
City underwater
Quotes
Inconcivable princess bribe
Catapulte me
Hang gliding
Water rafting
Leap of faith
Zipline
Snowboard down
Carriage 2 lanes with flasher
Fire boulders on lanes

## Dragon
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Randomize clouds
Activate prefabs so all tiles are there when you fly off and they do not pop.
Try blocking end of valley view with a cloud
Improve look of dragon's lair
Improve positioning of coins
Add storm effects
Add wind currents that make it harder
Hide secret loot, coins and passages in the clouds
Code resurrect if you die while flying
Code avoid obstacle left right linked to swipe left right
Make things go on fire if you breathe fire on them
Roast flying chicken in the air and if you collect/eat it, you have a bonus
Finish eject player sequence
Possibly code nice take off
Add flying birds in the scene
Warn player with sign catapult ahead and throw cannonballs at dragon
Have player yell a woohoo of excitement when he flies off on the dragon for the first time
Environment 1: winding valley with river at the bottom
Environment 2: Ocean with avatar style islands. You can land on certain islands or they may have catapults
Environment 3: Wintery mountain top where the King's castle lies. They are strong wind currents, snow and other dangerous obstacles.
Code tutorial flying and other dragon controls
Montgolfier with goblin that attack you

## Bezier
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Code lane switching
On exit of bezier curve, set current lane and desired lane
Small orientation glitch when swithing from one bezier curve to the next
EDITOR | Add gizmo to control points; fix little gap at the end;
Try replacing left and right invisible walls by distance to curve code
For now, prevent moveToSide when on curve
Angle on curve is slightly off esp. When chained or possibly because angle is more acute
No bezier as normal turn confusing
Small bezier turn or else jump feels weird

## Coin pickup
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Have star with total animate up then float down
Possibly allow for multiple stars with totals to appear
Create money bag with a light glow on pick up
change drop shadow label color to not black
normal vs end of series coins have different pick up sounds
Coin total icon header scales up and down each time coin amount changes
Review star placement system:
Ability to control spawn probability per level
Placed adequately, not on top of stumbles for example
ability to have series that bend around corners
ability to estimate in level data the number of coins
ability to know the real number of coins spawned
ability to control coin series type
ability to put on top of some obstacles like a log
ability to add to the sky

## Map
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Support multiple friend portraits per level that slide like in Candy Crush
Code friend pictures linked to level progress
Do real map
Have nice icons for shield and such
Possibly use color to indicate something about the level (theme, difficulty, has a dragon, whatever)

## Succubus
Category | Task | Description | Status | Time estimate | Time remaining | Phase | Notes
Create a special road segment for the succubus which is appropriate for spells
Finish coding chicken spell

## Achievements
| Achievement ID |  | Points
Watch your step |  | Stepped on a zombie's head.
Barrel crusher |  | Smash 500 barrels
Marathon man |  | Ran 42000 meters
Millionaire club |  | Collected 1000000 coins
Chicken Chaser |  | Kicked 20 chickens
Jumping Jack |  | Jumped 1000 times
Used magical boots
Used light wand
Finished a section like mountain of doom
Used detour
Used potion of see magic
A hell of a day |  | Went to hell
Dragon rider |  | Flew a dragon
Collected 1000 coins
Novice Runner |  | Ran 500 meters
Earned 3 stars on ALL levels
Reached the castle and saved the world
Zombie bowling : slide into 3 consecutive zombies
Bit by a zombie: a zombie killed you

## Zombies
Bug number | Description | Device | Status | Time estimate | Time remaining | Priority
Code zombie wave patterns
Add effect (texture or particle) when zombie burrowing out of the ground
Consider having zombie do an attack when the player is sufficiently close
At the beginning of a wave, have the succubus make a funny comment
Is your family ready for a zombie infestation?
Rule #33: when all else fails, summon zombies
Cemetery light casting zombie shadow in front of crypt with cutscene camera
| Zombie points icon |  | instead of star icon

## Detour
Bug number | Description | Device | Status | Time estimate | Time remaining | Priority
Single lane path
Higher loot, higher risk
Occasional bezier
Show only active tiles
Consider twilight land
Allow 1 detour per road segment
Use invisibility potion to see magic gates
| Bug: cannot exit left +lane limit Z error - currently commented out |  |  |  |  | HIGH
Make sure player arrives in center lane after turning into detour
Test detour when turning both left and right at T-Junction
Tile: slide under branch
Tile: slide over big dead tree
Tile: river crossing - one lane
Twilight: giant magic mushroom" Land on them and you fall asleep after puff of particles.
Put warning sign with skull

## Candy Crush
Bug number | Description | Device | Status | Time estimate | Time remaining | Priority
Share on Facebook when player completes a level
Post screenshot as custom story
Went to hell
Dragon flight
Change polling every 30 seconds of app request in world map to less frequent number
Should I cap number of lives?
Should I delete duplicate unlock request for same level from same person - see what candy crush does
Finish coding unlock next section
Should I implement live timers and unlock side missions for those who do not use facebook
Use iTween to pop-up display
Brag: Regis just beat your high score
display message/cut-scene scary portal in the sky when episode complete Little train icon
when 3 friends have accepted, do a glitz anim, move train, blink next shield
cap app requests to 99 drop older ones

## Endless zombie waves
Endless
Call of duty style staty alive for as many waves as you can
Unlocked at the end of the game
Number of waves leaderboard